Ageing Well Action Plan – Update: June 2025

PRIORITY AREA; Number of actions:; Completed:; On track:; Reassess due date:; Other:. Communication And Information; 8; 3; 2; 0; 1 - not started 2 - no longer progressing. Engagement And Inclusion; 8; 5; 2; 1; 0. People, Spaces and Places; 15; 2; 12; 0; 1 – not started. Civic Involvement, Volunteering and Retirement; 4; 0; 3; 0; 1 – not started. Cross-Cutting Support; 5; 4; 0; 1; 0. TOTALS; 40; 14 (35%); 19 (47.5%); 2 (5%); 5 (12.5%). Communication and Information

1 We will work to provide opportunities for people in South Ayrshire to get information, support, and advice in the right place and at the right time.

| Action | Lead Officer | Due Date | Progress | Latest Update |
| --- | --- | --- | --- | --- |
| Develop and share 'All About Me' booklets across South Ayrshire which will allow people to better plan for their future. | Marie Oliver | 30-Sep-2025 | 100% | 02-Jun-2025 Update provided by Marie Oliver: Big Cheerio took place on the 28th May. New over to you pack produced and already lots of interest. Will continue to give presentations to groups etc from October onwards. |
| We will continue to produce and distribute Strictly Seniors magazine across South Ayrshire. | Phil White | 30-Sep-2025 | 70% | 02-Jun-2025 This is an annual magazine, development of the 2025 edition will commence in due course. |
| We will explore opportunity to promote information in key public places such as at bus stops. | Phil White | 30-Sep-2025 | 0% | 02-Jun-2025 Update provided by Phil White: There is currently no progress in this area. |
| We will work to deliver on our ambitions to create a central point of information through the development of the 'Connect South Ayrshire' website, telephone number and physical spaces in each locality. | Steven Kelly | 30-Sep-2025 | 50% | 02-Jun-2025 This work continues to progress. A detailed update will be provided at the Ageing Well Board Meeting on 12th June 2025. |
| We will look for ways we can promote Income Maximisation for older people. | Marie Oliver | 30-Sep-2025 | 0% | 04-Feb-2025 Update provided by Marie Oliver: Funding for this post is no longer part of the HSCP contact. |
| We will support provide support for people being discharged from hospital to be signposted to the services and supports they need. | Steven Kelly | 30-Sep-2025 | 0% | 04-Feb-2025 Update provided by Steven Kelly: The VASA post that was in place is no longer being funded. |
| We will work to deliver an 'Over To You' box which supports healthy ageing and self-management. | Phil White | 31-Mar-2025 | 100% | 02-Jun-2025 Update provided by Phil White: Over to You resource launched on 28th May at Big Cheerio Event. |
| We will work to influence primary care providers to ensure they can provide appropriate and up-to-date wellbeing information. | Vivienne Forbes | 30-Sep-2025 | 100% | 04-Jun-2025 Update provided by Vivienne Forbes: This work is ongoing, continued work to engage with GP's on the Ageing Well agenda is underway via the GP forum. |

Engagement and Inclusion

02 We will listen to older people and continue to engage and offer opportunities to support older people to Age Well

| Action | Lead Officer | Due Date | Progress | Latest Update |
| --- | --- | --- | --- | --- |
| We will continue to support and facilitate the key role of the Champions Boards across South Ayrshire | Marie Oliver | 30-Sep-2025 | 100% | 02-Jun-2025 Update provided by Marie Oliver: Champions Board continues to grow and develop and taking forward actions. |
| We will work to ensure our communications meet accessibility standards | Rachael Graham | 30-Sep-2025 | 20% | 02-Jun-2025 We are working continually to improve accessibility standards in our documents. |
| We will look to develop our 'What You Can Do To Age Well' resource into an Ageing Well Toolkit in collaboration with partners. | Phil White | 30-Jun-2025 | 100% | 03-Apr-2025 Update provided by Phil White: The Ageing Well Toolkit has now been developed through Dumfries and Galloway is available for use as an online resource. |
| We will develop a team of Ageing Well Peer Educators to support older people in our communities. | Phil White | 30-Jun-2025 | 30% | 02-Jun-2025 Update provided by Phil White: We are awaiting a funding decision by the end of June from Alliance Scotland to allow this to progress. |
| We will explore how we can use innovative ideas such as interactive game development to raise awareness of issues for older people such as Frailty. | Phil White | 30-Apr-2025 | 10% | 02-Jun-2025 Update from Phil White: No further progress currently in this area, awaiting information from the lead organisation. Reassess due date |

03 We will look to consider inter-generational opportunities to bring older and younger people together

| Action | Lead Officer | Due Date | Progress | Latest Update |
| --- | --- | --- | --- | --- |
| We will look to bring together people from different age groups to encourage conversations and shared activities | Marie Oliver | 30-Sep-2025 | 100% | 02-Jun-2025 Update provided by Chair of the Intergenerational Joint Action Group: Our next Intergenerational Event will take place at Girvan Academy on the 4th of October in partnership with Girvan Youth Trust and Thriving Communities. Work is also taking place with communities in Annbank, Tarbolton and Mossblown to deliver an intergenerational project between school pupils and older residents. This will involve a roadshow taking place where people of all generations will discuss and look at photos from throughout their local history, as well as a filmmaking project wherein young people will interview older members of their community. VASA also took action throughout Intergenerational Week in April to share existing case studies previously sent to us and to promote intergenerational collaboration to those not already considering it. Several groups and schools have been in touch to pursue intergenerational work as a result of this awareness campaign. |

04 We will look for opportunities for maximise the use of technology to support Ageing Well

| Action | Lead Officer | Due Date | Progress | Latest Update |
| --- | --- | --- | --- | --- |
| We will continue to promote training and resources support for digital skills, digital literacy, and inclusion. | Marie Oliver | 30-Sep-2025 | 100% | 02-Jun-2025 Update provided by Marie Oliver: Digital Support Officer continues to be in high demand for drop in and 1-2-1 sessions. There has been excellent feedback. |
| We will ensure the Ageing Well movement is considered as part of our local Digital Strategies. | Thomas Griffin | 30-Sep-2025 | 100% | 02-Jun-2025 Update provided by Thomas Griffin: Work is ongoing to support the Ageing Well agenda from a digital perspective and this is business as usual. The new Technology Enabled Care Plan for South Ayrshire, a key work strand in the digital strategy, is being presented to Ageing Well Board on 12th June 2025 for comment and will be circulated to the Champions Board for information and further discussion. |

People, Places and Spaces

05 We will ensure our planning and strategies consider perspectives of older people

| Action | Lead Officer | Due Date | Progress | Latest Update |
| --- | --- | --- | --- | --- |
| We will work to ensure the development of Place Plans considers the views of older people in our communities and promote Ageing Well principles and activity. | Jamie Tait/Audrey Gatt | 30-Sep-2025 | 60% | 02-Jun-2025 Update provided by Audrey Gatt: The majority of localities in South Ayrshire either have a community-led action plan or are at different stages in developing one. The place planning consultation process is positive and has seen considerable improvement over previous response rates. Percentage rates that are relevant for the Ageing Well Strategy: the average participation of respondents from all current consultation, aged 51 to 69 is 42% and 70+ is of 20%. The opinions and recommendations of the age group above 51 years of age is therefore well represented. Thriving Communities have launched a new online platform Your Area Your Voice Your Choice will assist with engagement and consultation moving forward. |
| We will ensure our strategies and plans are aligned to the Ageing Well Movement including those on dementia, mental health and carers. | Rachael Graham | 30-Sep-2025 | 100% | 02-Jun-2025 This is now business as usual and Ageing Well is considered across all strategic work areas in the HSCP. |
| We will support the roll out and implementation of the Integrated Impact Assessment which considers how proposed changes will impact on our ageing communities. | Susan McCardie | 30-Sep-2025 | 100% | 18-Feb-2025 The IIA has now been implemented following Cabinet approval in September 2024. Monitoring updates will be provided to Service and Partnerships Performance Panel and this will include assessing impacts across all areas identified which will include our Ageing Population cross-cutting issue. These update reports will be shared with the Ageing Well Board going forward once they have been submitted to Service and Partnership Performance Panel for scrutiny. |
| We will promote the importance and opportunities linked to green spaces in our communities. | Eileen McCutcheon | 30-Sep-2025 | 50% | 04-Jun-2025 Update provided by Eileen McCutcheon: Blue health prescribing project will link with Community Links practitioners and GP practices for delivery. Green and blue health calendars available in hard copy and online https://www.greenhealthsa.org.uk/ and The Blue Health Calendar. Blue Health calendar launch and Earth Hour events took place March 2025. NHS/TCV operating green gym at Ailsa Hospital. Green health webpage Green Health - NHS Ayrshire & Arran. |

06 We will continue to build on existing work and develop a more comprehensive approach

| Action | Lead Officer | Due Date | Progress | Latest Update |
| --- | --- | --- | --- | --- |
| We will explore how we can facilitate the Take a Seat campaign in South Ayrshire to encourage older people to have confidence to venture into the community. | Marie Oliver | 30-Sep-2025 | 50% | 02-Jun-2025 Update provided by Marie Oliver: Flyers and window stickers now in place. Three businesses already signed up. By push on this activity over the summer months. |
| We will consider how we can develop better access to public facilities including toilets. | Marie Oliver | 30-Sep-2025 | 15% | 02-Jun-2025 Update provided by Marie Oliver: A mapping exercise is still underway will a directory completed by the end of August. |
| We will join together existing relevant work linked to our coastal areas (eg promenades) to develop a more coherent age friendly coastal area proposition. | Phil White | 30-Sep-2025 | 25% | 02-Jun-2025 Update provided by Phil White: Ageing Well are now represented on the Community Action Group - this is a stakeholder group informing the development of the Ayrshire Link. |

07 We will look to influence our partners and organisations to consider how their services could better support older people in the community

| Action | Lead Officer | Due Date | Progress | Latest Update |
| --- | --- | --- | --- | --- |
| We will seek to improve transport co-ordination to enable service users to experience more seamless provision and explore how we can connect people in their communities to support each other in relation to transport | Phil White | 30-Sep-2025 | 10% | 21-Jan-2025 Next Transport Workshop to take place in early 2025 to develop clear actions and timetable |
| We will seek to explore ways to improve the organisation of leisure opportunities for older people supported by local transport linkage to encourage greater use. | Phil White | 30-Sep-2025 | 10% | 21-Jan-2025 Next Transport Workshop to take place in early 2025 to develop clear actions and timetable |

08 We will maintain access to at least one socialising space for older people within each neighbourhood in South Ayrshire

| Action | Lead Officer | Due Date | Progress | Latest Update |
| --- | --- | --- | --- | --- |
| We will continue to support the creation and continuation of socialising spaces for older people in our communities. | Phil White | 30-Sep-2025 | 20% | 02-Jun-2025 Update provided by Phil White: There is new funding allocated via VASA from Scottish Government Community Mental Health and Well Being Funding with a proportion allocated to support Chatty Spaces. |

09 We will start to consider housing options to meet the needs of the ageing population

| Action | Lead Officer | Due Date | Progress | Latest Update |
| --- | --- | --- | --- | --- |
| We will explore how we could make better use of the current Sheltered Housing infrastructure to support Ageing Well. | Phil White | 30-Sep-2025 | 15% | 02-Jun-2025 Update provided by Phil White: A session planned for mid-May had to be re-organised as key people were unable to attend. Laura Thompson (SAC housing strategy) has carried out some background analysis of the present Sheltered Housing establishment. |
| We will support the development of the proposed Ageing Well Village in Ayr. | Billy McClean | 30-Sep-2028 | 0% | 02-Jun-2025 Update provided by Billy McClean: There has been no further progress in this area at the moment. |
| We will look to take forward recommendations from Planning for Prevention work with Vicky McCall which considers housing and ageing. | Phil White | 30-Sep-2025 | 10% | 02-Jun-2025 Update provided by Phil White: Recommendations made and require further discussion to be taken forward. |

10 We will consider how we can build on and sustain successful innovations for bringing older people together

| Action | Lead Officer | Due Date | Progress | Latest Update |
| --- | --- | --- | --- | --- |
| We will introduce 'Chatty Benches' across South Ayrshire with a view to reducing social isolation. | Marie Oliver | 30-Sep-2025 | 15% | 02-Jun-2025 Update provided by Marie Oliver: This is currently outstanding due to lack of funds for volunteer expenses etc. |

11 We will start to encourage conversations with commercial sector to build better informal spaces for older people

| Action | Lead Officer | Due Date | Progress | Latest Update |
| --- | --- | --- | --- | --- |
| We will engage with representative organisations and with individual commercial outlets to identify how they might support the Ageing Well vision. | Phil White | 30-Sep-2025 | 15% | 02-Jun-2025 Update provided by Phil White: Ahead of the curve team now have outreach presence in Ayr Wetherspoons to support people in the community. |

Civic Involvement, Volunteering and Retirement

12. We will extend options for older people in relation to paid work and volunteering.

| Action | Lead Officer | Due Date | Progress | Latest Update |
| --- | --- | --- | --- | --- |
| We will encourage organisations to become Age Friendly Employers and consider employment opportunities for older or retired people. | Phil White | 30-Jun-2025 | 10% | 02-Jun-2025 Update provided by Phil White: There has been no further progress in this area. |
| We will promote the importance of volunteering and engaging in community activities. | Phil White | 30-Sep-2025 | 0% |  |
| We will work to develop a pre-retirement Ageing Well course. | Phil White | 30-Jun-2025 | 25% | 02-Jun-2025 Update provided by Phil White: A meeting has been convened of key HR staff at both NHS and Council to start discussions. This will be chaired by Billy McClean. |
| We will continue to learn from developments in the area of Ageing Well in Scotland, the UK and internationally, and look for ways we can utilise locally. As well as this we will share our learning across the UK and beyond | Phil White | 30-Sep-2025 | 45% | 02-Jun-2025 Update provided by Phil White: South Ayrshire continues to convene this loose network – recent meeting in May included input from Centre for Ageing Better on their recent impact study. There was also discussion regarding using the pre-election period to raise the issue of ageing with candidates, etc. |

Cross-cutting Support

13. We will ensure we have the right infrastructure and support in place to take forward our actions effectively.

| Action | Lead Officer | Due Date | Progress | Latest Update |
| --- | --- | --- | --- | --- |
| We will transition from an Ageing Well Board to an Ageing Well Implementation Oversight Board | Phil White | 30-Sep-2024 | 100% | 04-Feb-2025 Update provided by Phil White: This action is now complete. The Oversight Group is now up and running with meetings taking place every two months. |
| We will put in place robust and co-ordinated programme management of the Ageing Well agenda and ensure our Ageing Well implementation is well-articulated with HSCP/SAC and NHS | Phil White | 30-Sep-2025 | 100% | 02-Jun-2025 Update provided by Phil White: This is now ongoing. |
| We will be able to demonstrate how we are making an impact and develop an evaluation framework that sets out how we measure impact in short, medium and long-term using quantitative and qualitative measures. | Sally Amor | 30-Apr-2025 | 10% | 04-Feb-2025 Update provided by Sally Amor: Discussions are ongoing with Public Health in relation to their contribution in respect of evaluation. Progress has been made with plans to run table top sessions with research allies before the end of March 2025. Aims and scope to be scoped and invite list to be agreed/invites issued. Reassess due date |
| We will ensure our reporting on progress is appropriate for key stakeholder groups and that progress reporting is timeous and comprehensive. | Phil White | 30-Sep-2025 | 100% | 02-Jun-2025 Update provided by Phil White: This is now ongoing. |
| We will look to develop an Ageing Well Development Fund which is accessible to promote age related projects in South Ayrshire. | Phil White | 30-Apr-2025 | 100% | 03-Apr-2025 Update provided by Phil White: The Ageing Well Development Fund is now in place and live. A sub-group has been assembled to oversee the submissions, evaluate and make recommendations to the Oversight Group. Around 8 applications have already been received. |